## Slide 1: Project Planning
Introduction
Notes: <number>

## Slide 2
What is Project
Planning
Man is still the most extraordinary computer of all.
John Fitzgerald Kennedy, May 21, 1963
Notes: <number>

## Slide 3: Four Steps to Project Management
Defining a Project
Creating a Project Plan
Tracking and Maintaining a Project Plan
Closing a Project
Notes: <number>
Managing projects is a matter of keeping scope, shedule and resources in balance. Generally this means PLANNING, organizing and tracking a project's taks and identifying and scheduling resources to accomplish those tasks.
Scope - range of tasks required to accomplish project goals
Schedulel indicates the time and sequence of each task as well as the total project duration.
Resources- people and or equipment - these usually have
costs such as wages or operating expenses that may
need to be tracked
When scope, schedule and resources are in balance you have just the right amount of resources to accomplish all your project tasks on or before the project deadline.
There is no single correct way to manage a project. In
fact if you ask 10 project management experts to explain the best way, you will get 10 different answers
However, there are 4 basic steps to all management wisdom:
1. defining a project
2. creating the project plan
3. tracking and maintaining a project plan
4. closing a project
You can get many tools to help you with steps 2 and 3 and
we will look at some tools directly from Raytheon for this
purpose. There is really no tool (program) for step 1. And
most tools just save and store a project at its close.

## Slide 4: Project Definition
Notes: <number>
You need to carefully consider your project's goals, scope, and assumptions. Goals must be stated in clear and specific terms. The scope is the combination of all the goals plus the work required to accomplish the goals. Assumptions are your best guesses as to how relevant factors are likely to affect the duration and cost of specific tasks.

## Slide 5: The Project Plan
Project Schedule
In-stage and
end-stage
review points
personnel
structure
estimates
SQA
CM
Metrics
Standards
risk
Notes: <number>
A project plan is a shedule of tasks and estimated completion times for appliation development. A project plan includes tasks to be completed, tentative task assignments, staffing plans and computer resources needed for the project. From the staff and resource estimates, cost of development is computed. The costs are used in the financial analysis which occurs next.

## Slide 6: Why Projects Fail?
(1) Lack of clear, understandable specifications
(2) Poor documentation
(3) Poor communications
(4) Overambitious objectives
(5) Low quality, poor performance
(6) Never-ending development
(7) High costs and cost overruns
(8) Perpetual maintenance
Notes: <number>

## Slide 7
Planning Stages
Any new venture goes through the following stages: Enthusiasm, Complication, Disillusionment, Search for the Guilty, Punishment of the Innocent, and Promotion of the non-involved.
Anonymous
Notes: <number>

## Slide 8: Early Planning
1. Estimates
2. Project Schedule
3. List tasks. Include application development tasks, project specific tasks, interface organization tasks, and review and approval tasks
4. Identify the dependencies between tasks.
Notes: <number>

## Slide 9: Early Planning
5. Assign personnel either by name or by skill and experience level.
6. Assign completion times to tasks; compute the most likely time for each.
7. Identify the critical path.
Notes: <number>

## Slide 10
Estimating
There is only one thing about which I am certain, and that is that there is very little about which one can be certain.
W. Somerset Maugham, The Summing Up(1938)
Doubleday & Co., Inc., Mew York, NY
Notes: <number>

## Slide 11: Unknowns to Quantify Using a Software Development Model
Effort - measured in person-months, person-weeks, or person-years
Cost - derivable from the effort estimate
Duration - measured in months, weeks or years
Duration of each phase of the life cycle
Personnel requirements- How many people? When?
Notes: <number>

## Slide 12: Empirical Validation of Development Models
Data collection
software analyzers
report forms
interviews
Statistical interpretation of data
correlation techniques
exploratory studies
confirmatory studies
Notes: <number>

## Slide 13: Metrics and Models
Every metric measures the result of something or predicts something that will happen.
Metrics are the basis of models, and models describe the way the metrics correspond to each other and combine to describe the system as a whole.
Notes: <number>
For example, we can measure the number of seeded error found duning testing. Not only is this an absolute measurement, but it also predicts how many errors are left to be found in the system.
Measurement of several characteristics may tell us how fast we are progressing in terms of how much of the system is complete.

## Slide 14: Discussion
List examples of product metrics and process metrics.
Notes: <number>

## Slide 15: Code Metrics
A code metric is a measure that is
algorithmically determined from code
and that is used to characterize the
code.
Size Metrics
Data Structure Metrics
Logic Structure Metrics
Composite Metrics
Notes: <number>

## Slide 16: Size Metrics
operators
of
s
occurrence
Total
-
N
operands
unique
of
Number
-
operators
unique
of
Number
-
Code
of
Lines
-
LOC
1
2
1


Notes: <number>

## Slide 17: Size Metrics
)
(
log
N
V
2
1
2




x
2
1
N
N
N


total occurrences of operands.
size of the program in terms of the total number of tokens.
volume
N2
Notes: <number>

## Slide 18: Data Structure Metrics
vars
average variable span
average number of “live” variables
Notes: <number>

## Slide 19: Logic Structure Metrics
Cyclomatic complexity V(G)
De , Di
information flow metrics
Notes: <number>

## Slide 20: A Fortran subroutine that sorts an array into ascending order
Line Level
1 SUBROUTINE SORT (X,N)
2 INTEGER X (100) , N,I,J, SAVE, IM1
3 C THIS ROUTINE SORTS ARRAY X INTO ASCENDING
4 C ORDER.
5 IF (N.LT.2) GO TO 200 1
6 DO 210 I =2, N 2
7 IM1=I-1 3
8 DO 220 J=1, IM1 3
9 IF (X(I) .GE.X(J) GO TO 220 4
10 SAVE=X(I) 5
Notes: <number>

## Slide 21: A Fortran subroutine that sorts an array into ascending order
Line Level
11 X(I) = X(J) 5
12 X(J)= SAVE 5
13 220 CONTINUE 3
14 210 CONTINUE 2
15 200 RETURN 1
16 END
Notes: <number>

## Slide 22: A Token Analysis of Subroutine SORT
Operators Occurrences Operands Occurrences
SUBROUTINE 1 SORT 1
0 10 X 8
, 8 N 4
INTEGER 1 100 1
IF 2 I 6
.LT. 1 J 5
GO TO 2 SAVE 3
DO 2 IM1 3
= 6 2 2
- 1 200 2
Notes: <number>

## Slide 23: A Token Analysis of Subroutine SORT
Operators Occurrences Operands Occurrences
.GE. 1 210 2
CONTINUE 2 1 2
RETURN 1 220 3
end-of-line 13
14

1

51

1
N
13
2


42
2

N
Notes: <number>

## Slide 24: Composite Metrics
effort
V
D
E
difficulty
N
2
D
tokens
of
number
in
equation,
length
log
log
N
2
2
1
2
2
2
1
2
1
x
x
x
x










ˆ
Notes: <number>

## Slide 25: CS 680 Project Effort Estimate
2,200,258
10,578
208
ˆ
10,578
145)
(58
log
1380
ˆ
208
145
1041
2
58
ˆ
1380
145
log
145
58
log
58
ˆ
Then,
145
58,
ˆ
:
estimates
token
2
2
2
2
1












x
E
V
x
D
x
x
N


Notes: <number>

## Slide 26: CS 680 Project Effort Estimate
days
6.8
of
estimate
effort
an
to
leads
which
day
emd
324,000
day
hr
5
hr
min
60
min
sec
60
sec
emd
18


x
x
x
Notes: <number>

## Slide 27: The Uses of Estimates
to staff projects
to control or monitor project implementation
to select proposed projects for implementation
to schedule projects
to quote charges to users
to audit project success
Notes: <number>

## Slide 28: Methods for Early Effort Estimation
Use past experience, data from previous projects, intuition, averaging methods, Delphi technique.
Use Halstead’s metrics, function points, etc. (i.e., measure something else which leads to an effort estimation.)
Use formal models of effort estimation.
Notes: <number>

## Slide 29: Building A Metrics Model (Version 1.0)
1. Gather data on a variety of metrics.
2. Throw a number of metrics into a large bag
3. Shake the bag very hard to form a model.
4. Cross your fingers and hope that the model tells you something you don’t already know.
Notes: <number>

## Slide 30
Let’s build the BSU Excellent Metrics Model of Effort Estimation.
Notes: <number>

## Slide 31: Mathematical Models of the Software Development Process
where y may be total effort, development cost, quality, etc.
These models can be theoretical or statistical.
Theoretical: based upon hypothesized relationship among factors.
)
,
,
(
n
x
x
x
f
y
.
.
.
2
1

.
.
.
size
.
.
.
effort
2

Notes: <number>

## Slide 32: Mathematical Models of the Software Development Process
Statistical: results of data-driven, statistical analyses.
Composite: combination of above types.
.
.
.
size
.
.
.
effort
.438

.
.
.
size
1.5
.
.
.
effort
2
x

Notes: <number>

## Slide 33: Macro-models of Software Development
A macro-model is a relationship among factors generally supported by large-scale experiments.
Observation: larger projects generally are associated with lower average productivity.
Therefore, one cannot directly apply the results of micro-level studies to macro-level projects.
Notes: <number>

## Slide 34: Criteria for Judging a Model
validity
objectivity
ease of use
robustness
transportability
Notes: <number>

## Slide 35: Statistically Based Models
Linear models
SDC model
Farr and Zagorski
Nonlinear models
Walston-Felix
Bailey-Basili
Boehm
Doty
Notes: <number>

## Slide 36: Theoretically Based Models
Putnam’s resource allocation model
Jensen’s model
Software science effort model
Notes: <number>

## Slide 37: Composite Models
Putnam’s model
RCA PRICE S
COCOMO
SOFTCOST
COPMO
Notes: <number>

## Slide 38: COCOMO Estimation Tool
COoperative COst MOdel
Original Version by Barry Boehm, 1981.
USC COCOMO II can be used to estimate effort, schedule and cost required to develop a software product.
Also provides breakdown of effort and schedule into software life-cycle phases.
Notes: <number>

## Slide 39
Relative Product Multiplicative Factors
Turnaround time
Schedule const.
Lang. experience
Personnel capability
Product complexity
Reliability reqmts.
Timing const
Applic. exper
Modn prg prac
Software tools
Vm volatility
Notes: <number>

## Slide 40: COCOMO Cost Drivers
Product Attributes
Required Software Reliability
(RELY)
Data Base Size (DATA)
Product Complexity (CPLX)
Notes: <number>

## Slide 41: COCOMO Cost Drivers
Computer Attributes
Execution Time Constraint (TIME)
Main Storage Constraint (STOR)
Virtual Machine Volatility (VIRT)
Computer Turnaround Time (TURN)
Notes: <number>

## Slide 42: COCOMO Cost Drivers
Personnel Attributes
Analyst Capability (ACAP)
Application Experience (AEXP)
Programmer Capability (PCAP)
Virtual Machine Experience (VEXP)
Programming Language Experience (LEXP)
Notes: <number>

## Slide 43: COCOMO Cost Drivers
Project Attributes
Modern Programming Practices
(MODP)
Use of Software Tools (TOOL)
Required Development Schedule (SCED)
Notes: <number>

## Slide 44: COCOMO
COCOMO is also able to estimate cost and schedule for products that are built upon already existing code. Included factors are:
Adapted Source Lines of Code (ASLOC)
Percent of Design Modification (DM)
Notes: <number>

## Slide 45: COCOMO
Percent of Code Modification (CM)
Percent of Integration Required for Modified Software (IM)
Percent of reuse effort due to Software Understanding (SU)
Percent of reuse effort due to Assessment and Assimilation(AA)
Programmer Unfamiliarity with Software(UNFM)
Notes: <number>

## Slide 46
It's time for a
Demonstration!
Notes: <number>

## Slide 47: Some Underlying Equations
Review the effort estimation equation, p. 2
and the schedule estimation equation, p. 3
Notes: <number>

## Slide 48: Observations
Adjustments in “scale factors” replace the previous organic, semi-detached and embedded modes.
Seventeen effort multipliers play a dominant role in estimating PM.
Redoing code due to requirements volatility is incorporated (BRAK).
Notes: <number>

## Slide 49
Models Number and Type of Attributes
Size Data Base Complexity (8) (1) (10)
Farr-Zagorski 5 1 1
SDC 2 - 1
Aron - - 3
NADC 5 1 1
Putnam 2 - 3
Wolverton 1 - 3
GRC 1 - 1
Tecolote 1 - -
ESD 2 1 1
COCOMO 2 1 7
Daly 2 - 6
Aerospace 1 - 1
Walston-Felix 1 - -
Doty 2 - -
Kustanowitz 1 1 -
Price-S 2 - 1
Total 30 5 29
% 20 3 19
Notes: <number>

## Slide 50
Models Number and Type of Attributes
Type of Program Documentation Environment
(3) (3) (15)
Farr-Zagorsky - 2 3
SDC 1 1 6
Aron - - 1
NADC - 2 3
Putnam - - 2
Wolverton 1 - 4
GRC - - 2
Tecolote - - 1
ESD - - 2
COCOMO 3 - 12
Daly 1 1 5
Aerospace 1 - 1
Walston-Felix - - -
Doty 2 - 5
Kustanowitz - - 3
Price-S 2 - 4
Total 11 6 54
% 7 4 36
Notes: <number>

## Slide 51
Models Number and Type of Attributes
Other Items Total Attributes
(9) (49)
Farr-Zagorsky 1 13
SDC 1 12
Aron - 4
NADC 1 13
Putnam - 7
Wolverton 6 15
GRC - 4
Tecolote 1 3
ESD - 6
COCOMO 4 29
Daly 1 16
Aerospace - 4
Walston-Felix 1 2
Doty - 9
Kustanowitz - 5
Price-S 1 10
Total 17 152
% 11 100
Notes: <number>

## Slide 52: Steps in Building an Algorithmic Effort Estimation Model (Version 2.0)
1. Determine which factors (metrics) to collect to form an historical database.
2. Collect historical data over a period of years, on a number of projects.
3. Identify theoretical basis of model (what we believe to be true).
4. Acknowledge if SLOC (or function points) is the primary cost driver.
Notes: <number>

## Slide 53: Steps in Building an Algorithmic Effort Estimation Model (Version 2.0)
5. Determine which cost drivers (factors) are important to incorporate into a model. (Develop an m(x).)
6. Develop weights for cost drivers based on historical data.
7. Supplement theoretical model with data-driven components based on historical data (determine the model’s constants).
Notes: <number>

## Slide 54: Steps in Building an Algorithmic Effort Estimation Model (Version 2.0)
8. Test predictive qualities of model in home environment and transportability of model to other databases.
9. Determine if projects need to be categorized or model calibrated to get better statistical fit.
10. Determine if model is capable of predicting effort by phases of life cycle.
Notes: <number>

## Slide 55: Other Estimating Techniques
Algorithmic Methods
  relies on one or more key formulae
  five types
    linear
    multiplicative
    analytic
    tabular
    composite
Notes: <number>
All but the composite method are rarely used because they offer too simplistic a model of project work. The noncomposite methods do not support adjustment of the model for extertise of staff, tools or other factors that might alter the time and cost of development. All algorithmic methods suffer from the same FATAL FLAW that they rely on some initial estimate that is difficult to guess and on which the accuracy of the entire estimates rests.
Linear = A0 + A1X1 + ... AnXn A-weights X-Source of Costs
Multip = A0 +A1 to the x1 + ...
Analytic = Halsteads Model

## Slide 56: Other Estimating Techniques
Expert judgement
  Delphi
Analogy
Parkinson’s Law
Price-to-Win
Notes: <number>
expert judgement - experience cannot be taught to others
analogy - a recently completed project is selected to act as a prototype baselline - technique may work in larger companies with many similar projects, but it is not useful in small co., unique projects, or projects using new technology, methodology, or languages.
Parkinson's Law - Work expands to fill the time available(BAD)
Price-to-Win - consultant strategy, uses a low estimate to get the job with the implication that time and cost will be adjusted
any estimate is good as long as you get the job. forces compromise on application requirements to meet costs, gives co. a bad reputation, results in cost overruns for both time and money

## Slide 57: Other Estimating Techniques
Top-Down
Bottom-Up
Maximum-Acceptable-Sum-of-Cash-Having-Indicated-Sonic-Threshold
Notes: <number>
TD - used with one or more of the other estimating techniques. Then total cost is split among the components. After a time estimate is derived, the 40-20-40 rule is applied to the estimate. 40 - analysis and design 20 - coding and unit testing 40 - testing. Problem- low level technical problems not uncovered or overlooked
BU - each software component is identified and estimated and then summed up for a total. Problem is it takes longer to get an estimate, but based on a more detailed understanding of the project

## Slide 58: Advantages and Disadvantages of Estimating Techniques
Notes: <number>

## Slide 59: Advantages and Disadvantages of Estimating Techniques
Notes: <number>

## Slide 60
Advantages and Disadvantages of Estimating Techniques
Notes: <number>

## Slide 61: Guidelines to Better Estimates
assign initial estimating task to the final developers
delay accepting the initial estimate until the end of a thorough study
anticipate and control user changes
monitor the progress of the proposed project
Notes: <number>

## Slide 62: Guidelines to Better Estimates
rely on documented facts, keep historical data
evaluate proposed project progress by using independent auditors
use composite models
use more than one estimating method
Notes: <number>

## Slide 63: Augustine’s Law
“Software is like entropy. It is difficult to grasp, and obeys the Second Law of Thermodynamics; I.e., it always increases.”
Notes: <number>

## Slide 64: Function-Oriented Metrics
Use a measure of the functionality delivered by the application as a normalization value
Must be derived indirectly using other direct measures
Based on countable measures of the software’s information domain.

## Slide 65: Computing Function Points
The steps are:
(1) Count the number of
- user inputs
- user outputs
- user inquiries
- files
- external interfaces
(2) A complexity value is then associated with each count, resulting in what is called a count-total.

## Slide 66: Computing Function Points
(3) Then 14 questions are rated on a scale of 0 to 5, giving “complexity adjustment values” to the resulting function point metric. These questions are related to such characteristics as data communications, performance, end-user efficiency, reusability, installation ease, and desire to facilitate change.

## Slide 67: Computing Function Points
(4) Finally
FP = count-total x [.65 + .01 x  Fi]
Function points are used to normalize measures of software productivity and quality, such as errors/FP, $/FP, pages of doc/FP, and FP/pm.

## Slide 68: Function Point Sample Computation
We will now compute a function point metric count using a spreadsheet entitled Funcpt.xls.

## Slide 69: Relationships Between LOC and Function Point Metrics